Software Project Plan

Scope, Timeline, and Team Roles for a Sample Application

# Aim

To prepare a software project plan defining the scope, timeline, and team roles required to design, develop, and deploy a real-world sample software application.

# Objective

- Define the scope of the project, including inclusions and exclusions.

- Break down the project into phases with a realistic timeline.

- Identify the team roles and responsibilities required for successful delivery.

- Establish deliverables, milestones, and resource requirements for each phase.

# Selected Software Application

Telemedicine & Appointment Booking Platform (e.g., Practo/Apollo 24|7)

A Telemedicine and Appointment Booking Platform allows patients to register, search doctors by specialty, book appointments, consult via video call, make online payments, and access e-prescriptions and reports.

# 1. Project Scope

## In Scope

- Patient Module: Registration, Login, Doctor Search, Appointment Booking, Video Consultation, Online Payment, Prescription/Report Access.

- Doctor Module: Availability Management, Appointment Accept/Reject, Consultation, e-Prescription Issuance.

- Pharmacy Module: Prescription Order Receipt, Medicine Availability Check, Delivery Status Tracking.

- Admin Module: User Management, Doctor Verification, Reports, Analytics.

- Integration with third-party Payment Gateway and Video Conferencing APIs.

- Web application and mobile application (Android/iOS) front ends.

## Out of Scope

- In-person hospital management or inventory systems.

- Insurance claim processing and reimbursement workflows.

- Integration with legacy hospital ERP systems (planned for a future phase).

## Assumptions and Constraints

- Doctors and patients have access to smartphones/computers with stable internet connectivity.

- Third-party APIs (payment gateway, video conferencing) are available and stable.

- Project must comply with healthcare data privacy regulations (e.g., HIPAA/local equivalent).

- Delivery timeline is fixed at 6 months from project initiation.

# 2. Project Timeline

The project follows an Agile delivery approach with iterative sprints, organized under the major phases below.

| Phase | Key Activities | Duration | Deliverables |
| --- | --- | --- | --- |
| Requirement Analysis | Stakeholder interviews, SRS preparation, API/vendor selection | Weeks 1–2 | Software Requirement Specification (SRS) |
| System Design | Architecture, database schema, UI/UX design, API design | Weeks 3–4 | UML Diagrams, Database Schema, UI Mockups |
| Sprint 1: Core Modules | User registration/login, doctor search, admin setup | Weeks 5–7 | Working build – Auth & Search |
| Sprint 2: Appointments & Payments | Appointment booking, payment gateway integration | Weeks 8–10 | Working build – Booking & Payments |
| Sprint 3: Video Consultation | Video conferencing integration, e-prescription module | Weeks 11–13 | Working build – Consultation module |
| Sprint 4: Pharmacy & Admin | Pharmacy module, analytics dashboard, reports | Weeks 14–16 | Working build – Pharmacy & Admin |
| Testing (UAT) | Unit, integration, system, and user acceptance testing | Weeks 17–19 | Test Reports, Bug Fix Log |
| Deployment | Cloud deployment, mobile app release, go-live | Weeks 20–21 | Production Release |
| Maintenance | Bug fixes, security updates, feature enhancements | Weeks 22–24 (ongoing) | Maintenance Log, Patch Releases |

# 3. Team Roles and Responsibilities

| Role | Responsibilities | Count |
| --- | --- | --- |
| Project Manager | Planning, scheduling, stakeholder communication, risk management | 1 |
| Business Analyst | Requirement gathering, SRS documentation, sprint backlog grooming | 1 |
| UI/UX Designer | Wireframes, prototypes, and UI design for web and mobile apps | 1 |
| Solution Architect | System architecture, API design, technology stack decisions | 1 |
| Backend Developers | Development of Login, Appointment, Payment, and Pharmacy modules | 3 |
| Frontend Developers | React-based web UI and mobile application development | 2 |
| Video/Integration Engineer | Video conferencing API and payment gateway integration | 1 |
| QA/Test Engineers | Unit, integration, system, and UAT testing | 2 |
| DevOps Engineer | CI/CD pipeline, cloud deployment, monitoring | 1 |
| Database Administrator | Database design, optimization, and maintenance | 1 |

# 4. Milestones

| Milestone | Target Week |
| --- | --- |
| SRS Sign-off | Week 2 |
| Design Approval | Week 4 |
| Core Modules Demo | Week 7 |
| Payment Integration Complete | Week 10 |
| Video Consultation Module Complete | Week 13 |
| UAT Sign-off | Week 19 |
| Go-Live | Week 21 |

# 5. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Third-party API downtime (payment/video) | High | Select vendors with SLA guarantees; add fallback providers |
| Changing requirements mid-sprint | Medium | Agile sprint reviews and backlog re-prioritization |
| Data privacy/compliance gaps | High | Early legal/compliance review; encrypted data handling |
| Resource unavailability | Medium | Cross-training team members; maintain buffer resources |

# Conclusion

This project plan defines a clear scope, a phase-wise timeline of approximately six months, and well-defined team roles for developing the Telemedicine & Appointment Booking Platform. Following an Agile delivery model with defined milestones and risk mitigation strategies ensures the project remains on schedule, within scope, and adaptable to evolving patient and doctor requirements.